## Time Spent
TEAM STATUS REPORT

## Goals
Goals that We are working on to complete
Group | Date Completed
Programming
1. Learn GitHub | 2021-01-20
2. Design Database | Ongoing…
3. Entity Relationship Diagram | Ongoing…
4. Design flow of the program | Ongoing…
5. Fill Database in
6. Code program
Web Design
1. Learn GitHub | 2021-01-20
2. Design wireframe | 2021-01-31
3. Work on Logo | 2021-01-31
4. Pick color scheme | 2021-01-25
5. Design of Web Page | Ongoing…
6. Work on integrating webpage with program code
Micro Applications
1. Learn GitHub | 2021-01-20
2. Make bi-weekly Agendas | 1/31/2021 (1st)
3. Create a Progress Report bi-weekly | 1/31/2021 (1st)
4. Brochure Design | Ongoing…
5. Design technical manual.

## Program Code
Name | ERD Design | Database Planning | Program Coding | Meetings with Teachers | Individual Group Meetings | Total Number Hours
Colin | 4.5 | 1.5 |  | 1.25 | 2 | 9.25
Stacy | 4.5 | 1.5 |  | 1.25 | 2 | 9.25

## Web Designers
Name | Researching Templates & Logo | Web Page Design | Individual Group Meetings | Total Number Hours
Sarah | 4 | 4 | 3 | 11
Lamon | 4 |  | 3 | 7

## Micro Apps
Name | Database Planning | Meetings with Teachers | Individual Group Meetings | Brochure Design | Agenda Design & Status Report | Total Number Hours
Jeffery | 2 | 0 | 4 | 3 | 3 | 12
Patrick | 2 | 0.75 | 4 | 4 | 1.5 | 12.25

## Est of Completion of Code
Estimate of Completion of Program Code
Week | Percent Complete
Week 1
Week 2
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15

## Est. of Completion of Web Page
Estimate of Completion of Web Page
Week | Percent Complete
Week 1
Week 2
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15

## Est. of Completion of Tech Man.
Estimate Completion of Tech Manual
Week | Percent Complete
Week 1 | 0%
Week 2 | 0%
Week 3 | 0%
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15

## Est. of Completion of Brochure
Estimate Completion of Brochure
Week | Percent Complete
Week 1 | 5%
Week 2 | 10%
Week 3 | 50%
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15