## Program Code
Sprint Meeting 1
Sprint # | Name | ERD Design | Database Planning | Program Coding | Meetings with Teachers | Individual Group Meetings | Research | Total Number Hours
1 | Colin | 4.5 | 1.5 |  | 1.25 | 2 |  | 9.25
1 | Stacy | 4.5 | 1.5 |  | 1.25 | 2 |  | 9.25
Sprint Meeting 2
Sprint # | Name | ERD Design | Database Planning | Program Coding | Meetings with Teachers | Individual Group Meetings | Research | Total Number Hours
2 | Colin | 0.5 | 1 | 5 | 1 | 2 | 1 | 10.5
2 | Stacy | 0.5 | 1 | 3 | 1 | 2 | 2.5 | 10
Sprint Meeting 3
Sprint # | Name | ERD Design | Database Planning | Program Coding | Meetings with Teachers | Individual Group Meetings | Research | Total Number Hours
3 | Colin | 0 | 2.75 | 5.5 | 0 | 2.5 | 1 | 11.75
3 | Stacy | 0 | 0 | 5 | 0 | 2.5 | 1 | 8.5
3 | Deo |  |  | 3 |  | 1 | 2 | 6
Sprint Meeting 4
Sprint # | Name | ERD Design | Database Planning | Program Coding | Meetings with Teachers | Individual Group Meetings | Research | Total Number Hours
4 | Colin | 0 | 2 | 5 | 2 | 2 | 1 | 12
4 | Stacy | 0 | 2 | 5 | 4 | 2 | 2 | 15
4 | Deo | 0 | 2 | 6 | 2 | 2 | 0 | 12
Sprint Meeting 5
Sprint # | Name | ERD Design | Database Planning | Program Coding | Meetings with Teachers | Individual Group Meetings | Research | Total Number Hours
5 | Colin | 0 | 0 | 9.5 | 2 | 3 | 0 | 14.5
5 | Stacy | 0 | 0 | 6.5 | 4 | 3 | 0.75 | 14.25
5 | Deo | 0 | 0 | 7 | 2 | 2.5 | 0 | 11.5
Total Hours Worked
Sum | Name | ERD Design | Database Planning | Program Coding | Meetings with Teachers | Individual Group Meetings | Research | Total Number Hours
| Colin | 5 | 7.25 | 25 | 6.25 | 11.5 | 3 | 58
| Stacy | 5 | 4.5 | 19.5 | 10.25 | 11.5 | 6.25 | 57
| Deo | 0 | 2 | 16 | 4 | 5.5 | 2 | 29.5

## Web Designers
Sprint Meeting 1
Sprint 1 | Name | Logo Design | Research for Template | Web Page Design | Individual Group Meetings | Implementing Program | Total Number Hours
1 | Sarah | 0 | 4 | 2 | 3 | 0 | 9
1 | Lamon | 2.5 | 0 | 0 | 3 | 0 | 5.5
Sprint Meeting 2
Sprint 2 | Name | Logo Design | Research for Template | Web Page Design | Individual Group Meetings | Intergrate Program | Total Number Hours
2 | Sarah | 1 | 2 | 4 | 3 | 0 | 10
2 | Lamon | 2.5 | 1 | 2 | 2 | 0 | 7.5
Sprint Meeting 3
Sprint 3 | Name | Logo Design | Research for Template | Web Page Design | Individual Group Meetings | Intergrate Program | Total Number Hours
3 | Sarah | 0 | 1.5 | 3 | 2 | 1 | 7.5
3 | Lamon | 0 | 1.5 | 3 | 0 | 1 | 5.5
Sprint Meeting 4
Sprint 4 | Name | Logo Design | Research for Template | Web Page Design | Individual Group Meetings | Intergrate Program | Total Number Hours
4 | Sarah | 0 | 1.5 | 2 | 1 | 4 | 8.5
4 | Lamon | 2 | 1 | 1 | 0 | 2 | 6
Sprint Meeting 5
Sprint 5 | Name | Logo Design | Research for Template | Web Page Design | Individual Group Meetings | Intergrate Program | Total Number Hours
5 | Sarah | 0 | 3 | 3 | 1 | 2 | 9
5 | Lamon | 0 | 2 | 1 | 1 | 0 | 4
Total Hours Worked
Sum | Name | Logo Design | Research for Template | Web Page Design | Individual Group Meetings | Intergrate Program | Total Number Hours
| Sarah | 1 | 10.5 | 14 | 10 | 7 | 42.5
| Lamon | 7 | 5.5 | 7 | 6 | 3 | 28.5

## Micro Apps
Sprint Meeting 1
Sprint | Name | Database Planning | Meetings with Teachers | Individual Group Meetings | Brochure Design | Agenda Design & Status Report | Technical Manual | Total Number Hours
1 | Jeff | 2 | 0 | 4 | 3 | 3 |  | 12
1 | Patrick | 2 | 0.75 | 4 | 4 | 1.5 |  | 12.25
Sprint Meeting 2
Sprint | Name | Database Planning | Meetings with Teachers | Individual Group Meetings | Brochure Design | Agenda Design & Status Report | Technical Manual | Total Number Hours
2 | Jeff |  | 0.5 | 2 | 5 | 4 |  | 11.5
2 | Patrick |  | 1 | 2 | 1 | 4 | 8 | 16
Sprint Meeting 3
Sprint | Name | Database Propagation | Meetings with Teachers | Individual Group Meetings | Brochure Design | Agenda Design & Status Report | Technical Manual | Total Number Hours
3 | Jeff | 2 | 0 | 3 | 2 | 4 | 4 | 15
3 | Patrick | 3 | 0 | 3 | 0 | 4 | 4 | 14
Sprint Meeting 4
Sprint | Name | Database Propagation | Meetings with Teachers | Individual Group Meetings | Brochure Design | Agenda Design & Status Report | Technical Manual | Total Number Hours
4 | Jeff | 2.5 | 0 | 1.5 | 1 | 2 | 0.5 | 7.5
4 | Patrick | 3 | 0 | 0.5 | 0 | 1 | 3 | 7.5
Sprint Meeting 5
Sprint | Name | Database Propagation | Meetings with Teachers | Individual Group Meetings | Brochure Design | Agenda Design & Status Report | Technical Manual | Total Number Hours
5 | Jeff | 0 | 0 | 3 | 0 | 2 | 3 | 8
5 | Patrick | 0 | 0 | 3 | 0 | 2 | 6 | 11
Total Hours Worked on Syllabest Project
Sum | Name | Database | Meetings with Teachers | Individual Group Meetings | Brochure Design | Agenda Design & Status Report | Technical Manual | Total Number Hours
| Jeff | 6.5 | 0.5 | 13.5 | 11 | 15 | 7.5 | 54
| Patrick | 8 | 1.75 | 12.5 | 5 | 12.5 | 21 | 60.75

## Est of Completion of Code (hidden)
Estimate of Completion of Program Code
Week | Percent Complete
Week 1
Week 2
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15

## Est. of Completion of Web Page (hidden)
Estimate of Completion of Web Page
Week | Percent Complete
Week 1 | 5%
Week 2 | 10%
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15

## Est. of Completion of Tech Man.
Estimate Completion of Tech Manual
Week | Percent Complete
Week 1 | 0%
Week 2 | 0%
Week 3 | 0%
Week 4 | 5%
Week 5 | 20%
Week 6 | 25%
Week 7 | 35%
Week 8 | 40%
Week 9 | 45%
Week 10 | 50%
Week 11 | 60%
Week 12
Week 13
Week 14
Week 15

## Est. of Completion of Brochure
Estimated Completion of Brochure
Week | Percent Complete
Week 1 | 5%
Week 2 | 10%
Week 3 | 50%
Week 4 | 60%
Week 5 | 65%
Week 6 | 75%
Week 7 | 80%
Week 8 | 80%
Week 9 | 90%
Week 10 | 90%
Week 11 | 95%
Week 12 | 95%
Week 13
Week 14
Week 15

## Totals Time Spent
Total Hours Spent On Syllabest Project