## Time Spent
TEAM STATUS REPORT

## Goals
Goals and Progress
Group | Date Completed | Reoccuring
Programming
1. Learn GitHub | 2021-01-20
2. Design Database | Ongoing…
3. Entity Relationship Diagram | 2021-02-08
4. Design flow of the program | Ongoing…
5. Fill Database in | Ongoing…
6. Code program | Ongoing..
Web Design
1. Learn GitHub | 2021-01-20
2. Design wireframe | 2021-01-31
3. Work on Logo | 2021-01-31
4. Pick color scheme | 2021-01-25
5. Design of Web Page | Ongoing…
6. Work on integrating webpage with program code
Micro Applications
1. Learn GitHub | 2021-01-20
2. Make bi-weekly Agendas | 1/31/2021 (1st) | 2/15/2021 (2nd)
3. Create a Progress Report bi-weekly | 1/31/2021 (1st) | 2/15/2021 (2nd)
4. Brochure Design | Ongoing…
5. Design technical manual. | Ongoing…

## Program Code
Sprint # | Name | ERD Design | Database Planning | Program Coding | Meetings with Teachers | Individual Group Meetings | Research | Total Number Hours
1 | Colin | 4.5 | 1.5 |  | 1.25 | 2 |  | 9.25
1 | Stacy | 4.5 | 1.5 |  | 1.25 | 2 |  | 9.25
Sprint # | Name | ERD Design | Database Planning | Program Coding | Meetings with Teachers | Individual Group Meetings | Research | Total Number Hours
2 | Colin | 0.5 | 1 | 5 | 1 | 2 | 1 | 10.5
2 | Stacy | 0.5 | 1 | 3 | 1 | 2 | 2 | 9.5
Sum | Name | ERD Design | Database Planning | Program Coding | Meetings with Teachers | Individual Group Meetings | Research | Total Number Hours
| Colin | 5 | 2.5 | 5 | 2.25 | 4 | 1 | 19.75
| Stacy | 5 | 2.5 | 3 | 2.25 | 4 | 2 | 18.75

## Web Designers
Sprint | Name | Logo Design | Research for Template | Web Page Design | Individual Group Meetings | Implementing Program | Total Number Hours
1 | Sarah | 0 | 4 | 2 | 3 |  | 9
1 | Lamon | 2.5 | 0 | 0 | 3 |  | 5.5
Sprint | Name | Logo Design | Research for Template | Web Page Design | Individual Group Meetings | Intergrate Program | Total Number Hours
2 | Sarah | 1 | 2 | 4 | 3 |  | 10
2 | Lamon | 2.5 | 1 | 2 | 2 |  | 7.5
Sum | Name | Logo Design | Research for Template | Web Page Design | Individual Group Meetings | Intergrate Program | Total Number Hours
| Sarah | 1 | 6 | 6 | 6 |  | 19
| Lamon | 5 | 1 | 2 | 5 |  | 13

## Micro Apps
Sprint | Name | Database Planning | Meetings with Teachers | Individual Group Meetings | Brochure Design | Agenda Design & Status Report | Technical Manual | Total Number Hours
1 | Jeff | 2 | 0 | 4 | 3 | 3 |  | 12
1 | Patrick | 2 | 0.75 | 4 | 4 | 1.5 |  | 12.25
Sprint | Name | Database Planning | Meetings with Teachers | Individual Group Meetings | Brochure Design | Agenda Design & Status Report | Technical Manual | Total Number Hours
2 | Jeff |  | 0.5 | 2 | 4 | 3 |  | 9.5
2 | Patrick |  | 1 | 2 | 1 | 3 | 3 | 10
Sum | Name | Database Planning | Meetings with Teachers | Individual Group Meetings | Brochure Design | Agenda Design & Status Report | Technical Manual | Total Number Hours
2 | Jeff | 2 | 0.5 | 6 | 7 | 6 | 0 | 21.5
2 | Patrick | 2 | 1.75 | 6 | 5 | 4.5 | 3 | 22.25

## Est of Completion of Code
Estimate of Completion of Program Code
Week | Percent Complete
Week 1
Week 2
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15

## Est. of Completion of Web Page
Estimate of Completion of Web Page
Week | Percent Complete
Week 1 | 5%
Week 2 | 10%
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15

## Est. of Completion of Tech Man.
Estimate Completion of Tech Manual
Week | Percent Complete
Week 1 | 0%
Week 2 | 0%
Week 3 | 0%
Week 4 | 5%
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15

## Est. of Completion of Brochure
Estimate Completion of Brochure
Week | Percent Complete
Week 1 | 5%
Week 2 | 10%
Week 3 | 50%
Week 4 | 60%
Week 5 | 65%
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15